## Sheet1
S.no | Date | Url | Issue related | Issue description | Screenshot | Browser | Priority | Tested by | Status
1 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Cicking on review button without filling texts in the fields error occurs | https://prnt.sc/qng5uf | Google Chrome | High | Jaswinder | Fail
2 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Alignment issue | https://prnt.sc/qng6t6 | Google Chrome | Low | Jaswinder | Fail
3 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Dummy text on the website | https://prnt.sc/qng8gy | Google Chrome | Medium | Jaswinder | Fail
4 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Clicking on chat with us design issue appears as black outlining | https://prnt.sc/qng9l4 | Google Chrome | Medium | Jaswinder | Fail
5 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Title should be details | https://prnt.sc/qngahr | Google Chrome | Medium | Jaswinder | Fail
6 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Mortgage calculator not working and accepting negative numbers | https://prnt.sc/qngbft | Google Chrome | High | Jaswinder | Fail
7 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Already filled email id still error appearing write email id and name | https://prnt.sc/qngcic | Google Chrome | High | Jaswinder | Fail
8 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Social icons not working and url adds with the # sign | https://prnt.sc/qngdkl | Google Chrome | High | Jaswinder | Fail
9 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | All the design has been misaligned | https://prnt.sc/qngfdj | I phone 6 | High | Jaswinder | Fail
10 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | These titles will be confusing for the user as scroll bar is not appearing but we are able to scroll | https://prnt.sc/qngg5j | I phone 6 | High | Jaswinder | Fail
11 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Menu button not working | https://prnt.sc/qngh82 | I phone 6 | High | Jaswinder | Fail
12 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Functionality | Buttons not working | https://prnt.sc/qnghv4 | I phone 6 | High | Jaswinder | Fail
13 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Design issue in reviews progress | https://prnt.sc/qngiv4 | I phone 6 | Medium | Jaswinder | Fail
14 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | No alignment of the box | https://prnt.sc/qngjjc | I phone 6 | High | Jaswinder | Fail
15 | 14.1.2020 | https://plotsinwaveestatemohali.in/properties/apartment-for-sale-quality/ | Design | Alignment issue | https://prnt.sc/qngl1r | I phone 6 | Medium | Jaswinder | Fail